## Summary
Acceptance Test Report — iW-ASCEJ-01-ATR-R1.0-REL1.0
Package iW-ASCEJ-01-DF-R1.0-REL1.0 (software 1.2.5). Automated results were recorded from the logs in 01_Logs. Bench results are entered on the Bench Record sheet (yellow cells).
Document | iW-ASCEJ-01-ATR-R1.0-REL1.0
Procedure | iW-ASCEJ-01-ATP-R1.0-REL1.0
Package | iW-ASCEJ-01-DF-R1.0-REL1.0 / software 1.2.5
Automated run date | 05-Oct-2026
Automated run host | Ubuntu 24.04.4 LTS, Linux 6.18 x86-64, gcc 13.3.0, CMake 3.28.3, Qt 5.15.13
Class | Tests | PASS | FAIL | N/A / open | Status
Automated tests (TS)
Automated checks
Bench tests (BT)
Overall acceptance
Sign-off
Tested by
Witnessed by (customer)
Approved by

## Automated Results
Automated Results (TS)
One row per automated test. The check counts come from the log of each test (ctest -V output).
ID | Test | Suite / ctest name | Checks PASS | Checks FAIL | Result | Log file (01_Logs) | ctest / runner reported pass
TS-01 | Firmware DAC input routing | firmware/run_tests.sh |  |  |  | TS-01_firmware_dac_routing.log | yes
TS-02 | PCIe end-to-end, firmware 1.2.1 | pcie_emu / pcie_e2e_fw_1_2_1 |  |  |  | TS-02_pcie_emu_pcie_e2e_fw_1_2_1.log | yes
TS-03 | PCIe end-to-end, firmware 1.2.0 (not reflashed) | pcie_emu / pcie_e2e_fw_1_2_0 |  |  |  | TS-03_pcie_emu_pcie_e2e_fw_1_2_0.log | yes
TS-04 | Host transmit path | gui / tx_path |  |  |  | TS-04_gui_tx_path.log | yes
TS-05 | Simulated RF loopback | gui / sim_loopback |  |  |  | TS-05_gui_sim_loopback.log | yes
TS-06 | H2C / RFDC control window | gui / control_window |  |  |  | TS-06_gui_control_window.log | yes
TS-07 | Whole application, simulation | gui / app_loopback |  |  |  | TS-07_gui_app_loopback.log | yes
TS-08 | Real iwfg_h2c with emulated card | h2c_emu / h2c_real_helper |  |  |  | TS-08_h2c_emu_h2c_real_helper.log | yes
TS-09 | Send-and-receive chain, fault injection | h2c_emu / loopback_chain |  |  |  | TS-09_h2c_emu_loopback_chain.log | yes
TS-10 | Whole application, live session, emulated card | h2c_emu / app_live_session |  |  |  | TS-10_h2c_emu_app_live_session.log | yes
Totals

## Check Detail
Check Detail
Every check printed by the automated tests, verbatim from the logs.
Test ID | # | Check (verbatim) | Result
TS-01 | 1 | refuses to touch the switch before it is initialised | PASS
TS-01 | 2 | ...and leaves it untouched | PASS
TS-01 | 3 | boot default routes successfully | PASS
TS-01 | 4 | boot default puts the DDS on the DAC (was: host) | PASS
TS-01 | 5 | select host | PASS
TS-01 | 6 | host selection puts the H2C stream on the DAC | PASS
TS-01 | 7 | readback reports host | PASS
TS-01 | 8 | select DDS | PASS
TS-01 | 9 | DDS selection puts the DDS on the DAC | PASS
TS-01 | 10 | readback reports DDS | PASS
TS-01 | 11 | rejects source 2 | PASS
TS-01 | 12 | rejects source -1 | PASS
TS-01 | 13 | an invalid request leaves the routing alone | PASS
TS-01 | 14 | disabled switch reads NONE | PASS
TS-01 | 15 | name: DDS | PASS
TS-01 | 16 | name: host | PASS
TS-01 | 17 | exactly one register commit per change | PASS
TS-02 | 18 | boot: the DAC plays the DDS | PASS
TS-02 | 19 | GUI attached to the emulated BAR | PASS
TS-02 | 20 | full sync: ping, identity, every register read back | PASS
TS-02 | 21 | snapshot returned 19 values | PASS
TS-02 | 22 | DAC stream clock read back: 200000 kHz (the generator's sample rate) | PASS
TS-02 | 23 | current firmware: no compensation | PASS
TS-02 | 24 | readback: DDS | PASS
TS-02 | 25 | GUI selects Host / GNU Radio stream | PASS
TS-02 | 26 | -> the DAC plays the host stream | PASS
TS-02 | 27 | -> the device confirms host | PASS
TS-02 | 28 | GUI selects DDS compiler | PASS
TS-02 | 29 | -> the DAC plays the DDS | PASS
TS-02 | 30 | -> the device confirms DDS | PASS
TS-02 | 31 | restore defaults | PASS
TS-02 | 32 | -> defaults put the DDS on the DAC | PASS
TS-02 | 33 | after defaults the panel shows what the DAC really plays (DDS) | PASS
TS-02 | 34 | DAC source 7 rejected: ACK error 0x5 | PASS
TS-03 | 35 | 1.2.0 boot: the DAC plays the host stream (the old bug) | PASS
TS-03 | 36 | GUI attached to the emulated BAR | PASS
TS-03 | 37 | full sync: ping, identity, every register read back | PASS
TS-03 | 38 | snapshot returned 19 values | PASS
TS-03 | 39 | DAC stream clock read back: 200000 kHz (the generator's sample rate) | PASS
TS-03 | 40 | old firmware detected from its capability word | PASS
TS-03 | 41 | readback shows the truth: the DAC is on the host stream (firmware itself claims DDS) | PASS
TS-03 | 42 | GUI selects Host / GNU Radio stream | PASS
TS-03 | 43 | -> the DAC plays the host stream | PASS
TS-03 | 44 | -> the device confirms host | PASS
TS-03 | 45 | GUI selects DDS compiler | PASS
TS-03 | 46 | -> the DAC plays the DDS | PASS
TS-03 | 47 | -> the device confirms DDS | PASS
TS-03 | 48 | restore defaults | PASS
TS-03 | 49 | -> 1.2.0 defaults put the host stream on the DAC (its bug), and the GUI will show that | PASS
TS-03 | 50 | after defaults the panel shows what the DAC really plays (host stream) | PASS
TS-03 | 51 | DAC source 7 rejected: ACK error 0x5 | PASS
TS-04 | 52 | DAC packing: bits[1:0] == 00 in every word (all waveforms) | PASS
TS-04 | 53 | DAC packing: ¦sample¦ <= 8191<<2 = 32764 | PASS
TS-04 | 54 | 10 MHz @ 200 MSPS, 4096-sample loop -> 10.009766 MHz (205 cycles) | PASS
TS-04 | 55 | 12.5 MHz fits the loop exactly -> unchanged | PASS
TS-04 | 56 | negative frequencies keep their sign (-7.324219 MHz) | PASS
TS-04 | 57 | coherence off -> exact request | PASS
TS-04 | 58 | looped chunk: tone at 10.009766 MHz | PASS
TS-04 | 59 | looped chunk: SFDR 93.1 dB (14-bit quantisation limited) | PASS
TS-04 | 60 | end to end, coherent: tone at 10.009766 MHz | PASS
TS-04 | 61 | end to end, coherent: SFDR 93.1 dB through the replay | PASS
TS-04 | 62 | end to end, NON-coherent (old behaviour): SFDR only 12.5 dB — the replay seams the test must detect | PASS
TS-04 | 63 | live update while running: now 20.019531 MHz (20 MHz requested) | PASS
TS-04 | 64 | transmitting() reports the new frequency | PASS
TS-04 | 65 | stop honoured in 10 ms | PASS
TS-04 | 66 | restart without recreating the generator | PASS
TS-04 | 67 | non-FIFO path: generator stops with an error | PASS
TS-04 | 68 | ...and is not left marked as running | PASS
TS-04 | 69 | ...and a second start is accepted (not silently ignored) | PASS
TS-04 | 70 | coherent loop written once (1 chunk(s) after 1 s) — nothing more for iwfg_h2c to copy | PASS
TS-04 | 71 | Stop sends a zero chunk: the replayed chunk is silence | PASS
TS-05 | 72 | DDS selected: tone at +9.9994 MHz (DDS 10 MHz, positive frequency) | PASS
TS-05 | 73 | DDS selected: tone 68.3 dB above the floor | PASS
TS-05 | 74 | DDS selected, generator running: DDS wins (+15.0000 MHz) | PASS
TS-05 | 75 | Host + generator: tone at +6.9825 MHz (generator transmits 6.982422 MHz) | PASS
TS-05 | 76 | Host + generator: tone 67.8 dB above the floor | PASS
TS-05 | 77 | Host + generator, 16 MiB loop: tone at +9.9994 MHz | PASS
TS-05 | 78 | Host + generator, negative tone: -4.9800 MHz | PASS
TS-05 | 79 | Host + square wave: fundamental at +4.0031 MHz | PASS
TS-05 | 80 | Host + square wave: harmonics present (SFDR 9.3 dB, a sine would be >40) | PASS
TS-05 | 81 | Host, nothing transmitting: no carrier (peak 34.4 dB over floor at +0.000 MHz — DC offset only) | PASS
TS-05 | 82 | DDS outside the displayed band: not aliased into view | PASS
TS-05 | 83 | ...and the status bar says why: "Simulated loopback: DDS 70.000 MHz is outside the displayed ±61.440 MHz band" | PASS
TS-05 | 84 | loopback off: modem demo still produced (mean power 0.246) | PASS
TS-06 | 85 | widgets found | PASS
TS-06 | 86 | combo items carry the logical PCIE_DAC_SRC_* values | PASS
TS-06 | 87 | simulation box shown in simulation mode | PASS
TS-06 | 88 | DAC input source usable with no device in simulation | PASS
TS-06 | 89 | select Host: loopback on, host source, nothing transmitting yet | PASS
TS-06 | 90 | Start generator (simulated): host running | PASS
TS-06 | 91 | tone 10 MHz -> published 9.999847 MHz with the 1024 KiB loop (what is really sent, within 381 Hz) | PASS
TS-06 | 92 | loop length = H2C buffer / 4 (262144 samples) | PASS
TS-06 | 93 | backend on 16 KiB: loop follows (4096 samples, 10.009766 MHz) | PASS
TS-06 | 94 | H2C link monitor present | PASS
TS-06 | 95 | 640.58 MiB/s flagged: "⚠ H2C link 640.6 MiB/s, but the DAC reads 762.9 MiB/s: it runs dry about 16% of the time a" | PASS
TS-06 | 96 | 762.9 MiB/s reported as keeping the DAC full | PASS
TS-06 | 97 | select DDS: published | PASS
TS-06 | 98 | Stop generator (simulated) | PASS
TS-06 | 99 | starting the generator in simulation routes the DAC to Host | PASS
TS-06 | 100 | leaving simulation stops the modelled generator | PASS
TS-06 | 101 | simulation box hidden in live mode | PASS
TS-06 | 102 | live, no device: DAC input source disabled (nothing to send to) | PASS
TS-06 | 103 | rdma_tx control block hidden outside RoCEv2 | PASS
TS-06 | 104 | ...and shown for RoCEv2 | PASS
TS-06 | 105 | Verify loopback button present | PASS
TS-06 | 106 | loopback follows the generator -> verified (inversion reported) | PASS
TS-06 | 107 | tone restored after the check (10.000000 MHz) | PASS
TS-06 | 108 | Received row: identifies the generator's tone | PASS
TS-06 | 109 | receiver stuck on the DDS -> NOT verified, cause named: "✗ The received tone did NOT move (it stayed at 10.000 MHz) when the generator mo" | PASS
TS-06 | 110 | display at the wrong rate -> reported as scaling, not as a transmit failure | PASS
TS-06 | 111 | live, not attached: says the DAC input could not be set (does not pretend) | PASS
TS-06 | 112 | live, no reader: state is "Waiting for iwfg_h2c…", not "Running" | PASS
TS-06 | 113 | stopped cleanly | PASS
TS-06 | 114 | Retry transmit and Capture 1 channel buttons exist | PASS
TS-06 | 115 | no backend: Retry transmit hidden | PASS
TS-06 | 116 | H2C playback row shows the helper state and why | PASS
TS-06 | 117 | backend running: Retry transmit offered | PASS
TS-06 | 118 | Retry transmit asks the main window to relaunch iwfg_h2c | PASS
TS-06 | 119 | C2H row: 2417 of 3052 MiB/s -> OVERLOADED, says it interrupts H2C | PASS
TS-06 | 120 | Capture 1 channel offered, disabled until RFDC attached | PASS
TS-06 | 121 | not attached: channel count left alone (PL GPIO cannot be set) | PASS
TS-06 | 122 | 1 channel, 760 of 763 MiB/s: no overload, button hidden | PASS
TS-06 | 123 | not live: C2H row says so | PASS
TS-07 | 124 | H2C CONTROL action present | PASS
TS-07 | 125 | control window opened | PASS
TS-07 | 126 | Host + generator: the received tone follows it -> "✓ Loopback verified. The generator moved 7.300 MHz and the tone received through the ADC moved 7.300" | PASS
TS-07 | 127 | DAC on the DDS: the check says the ADC is not seeing the generator, and why | PASS
TS-08 | 128 | 16 KiB chunks, 5 us per transfer: 593.4 MiB/s < 762.9 MiB/s the DAC reads — starved (the bench symptom) | PASS
TS-08 | 129 | 1 MiB chunks (the 1.2.4 default), same cost: 753.0 MiB/s — the DAC is kept fed | PASS
TS-08 | 130 | 16 MiB chunks, same cost: 768.0 MiB/s | PASS
TS-08 | 131 | DAC stream captured (3 loops, 284 ms from start incl. building the loop) | PASS
TS-08 | 132 | tone at 10.000038 MHz (requested 10 MHz, transmitted 9.999990) | PASS
TS-08 | 133 | across a loop seam: SFDR 90.8 dB — seamless, no interference | PASS
TS-08 | 134 | 16 MiB loop: 10 MHz lands within 9.5 Hz | PASS
TS-08 | 135 | written once: iwfg_h2c reports GR_updates=0/s after loading | PASS
TS-08 | 136 | tone changed to 23.450089 MHz while running | PASS
TS-08 | 137 | ...and is pure (SFDR 86.4 dB) | PASS
TS-08 | 138 | after Stop the card replays silence (peak 0.000000) | PASS
TS-08 | 139 | driver refuses 16 MiB: iwfg_h2c exits (code 1) without a rate line — launcher steps down | PASS
TS-08 | 140 | step-down ladder: 16 MiB -> 4 MiB -> ... -> 16 KiB -> stop | PASS
TS-08 | 141 | parses the bench line: 640.58 MiB/s, 48 updates/s | PASS
TS-08 | 142 | ignores other lines | PASS
TS-08 | 143 | default H2C buffer is 1 MiB | PASS
TS-08 | 144 | IWFG_H2C_CHUNK_BYTES overrides it | PASS
TS-08 | 145 | an invalid override is ignored | PASS
TS-09 | 146 | G both helpers load (c2h_stream: ok, iwfg_h2c: ok) | PASS
TS-09 | 147 | G pre-flight took 3 ms (1.2.3: ~6000 ms with the window frozen) | PASS
TS-09 | 148 | G pre-flight opened no device node | PASS
TS-09 | 149 | A backend ready (capture FIFO /tmp/loopback_emu_3881/c2h.fifo) | PASS
TS-09 | 150 | A iwfg_h2c launched with the 1 MiB default buffer (got 1048576) | PASS
TS-09 | 151 | A H2C playback reports Streaming | PASS
TS-09 | 152 | A iwfg_h2c's delivery reported to the GUI: 761.0 MiB/s (the DAC needs 762.9) | PASS
TS-09 | 153 | A 46137344 samples received through the loopback | PASS
TS-09 | 154 | A received tone 9.999847 MHz = transmitted 9.999847 MHz | PASS
TS-09 | 155 | A received tone is clean: SFDR 82.3 dB | PASS
TS-09 | 156 | A c2h_stream's own rate arrives live (160.0 MiB/s; stdbuf line buffering) | PASS
TS-09 | 157 | A no failure reported | PASS
TS-09 | 158 | H backend stopped (asynchronously) | PASS
TS-09 | 159 | H reader with no writer used 0.05 s CPU in 1.5 s (1.2.3 spun a whole core) | PASS
TS-09 | 160 | H the reader says it is waiting for the capture helper | PASS
TS-09 | 161 | B the launcher saw c2h_stream end and restarted it | PASS
TS-09 | 162 | B the reason is named (not just "exit 0") | PASS
TS-09 | 163 | B the reader re-attached to the new FIFO by itself | PASS
TS-09 | 164 | B data flows again after the restart (2818048 new samples) | PASS
TS-09 | 165 | B and it is the transmitted tone (9.999847 MHz, SFDR 82.3 dB) | PASS
TS-09 | 166 | B no fatal failure, no dialog | PASS
TS-09 | 167 | B transmit was not disturbed (iwfg_h2c launched once) | PASS
TS-09 | 168 | C stepped down 1 MiB -> 256 KiB and streams (state streaming) | PASS
TS-09 | 169 | C the step-down was reported | PASS
TS-09 | 170 | C it first reopened at the same size, and stepped down only when that stalled too | PASS
TS-09 | 171 | C the generator followed the new loop length; tone received 10.000610 MHz, SFDR 82.3 dB | PASS
TS-09 | 172 | C no failure dialog | PASS
TS-09 | 173 | D steps down to 16 KiB, then reports Stalled (not a size problem) | PASS
TS-09 | 174 | D iwfg_h2c is left running: it resumes by itself when the card consumes | PASS
TS-09 | 175 | D the operator is told what to check | PASS
TS-09 | 176 | D capture keeps running meanwhile (41943040 samples in 1 s) | PASS
TS-09 | 177 | D no dialog | PASS
TS-09 | 178 | K walked down to 16 KiB and reports Stalled | PASS
TS-09 | 179 | K once the card consumes, transmit is relaunched at the 1 MiB default (not left on 16 KiB) | PASS
TS-09 | 180 | K tone received 9.999847 MHz, SFDR 82.3 dB | PASS
TS-09 | 181 | K no dialog | PASS
TS-09 | 182 | P streaming again at 1 MiB after one same-size reopen (buffer 1024 KiB) | PASS
TS-09 | 183 | P no step-down (1.2.4 walked straight down the ladder) | PASS
TS-09 | 184 | P tone received 9.999847 MHz | PASS
TS-09 | 185 | N capture FIFO pipe buffer 1024 KiB (default 64 KiB; max allowed 1024 KiB) | PASS
TS-09 | 186 | M /dev/iwfg1 closed before /dev/iwfg0 (so the driver's QDMA reset runs on the last close) | PASS
TS-09 | 187 | O the capture stalled (c2h_stream waits in the driver) | PASS
TS-09 | 188 | O nothing arrives meanwhile (0 samples in 2 s) | PASS
TS-09 | 189 | O resetDevice() reported as begun | PASS
TS-09 | 190 | O ... and finished: capture and transmit restarted | PASS
TS-09 | 191 | O the reason is logged | PASS
TS-09 | 192 | O data flows again and it is the transmitted tone (9.999847 MHz) | PASS
TS-09 | 193 | O transmit streaming again | PASS
TS-09 | 194 | O no fatal failure | PASS
TS-09 | 195 | E backend ready | PASS
TS-09 | 196 | E stop() returned in 0 ms (1.2.3 blocked up to 10 s) | PASS
TS-09 | 197 | E stopped() after 5590 ms: SIGINT, SIGTERM ignored, SIGKILL worked | PASS
TS-09 | 198 | E the event loop kept running throughout (longest gap 49 ms) | PASS
TS-09 | 199 | E nothing left behind | PASS
TS-09 | 200 | F not refused | PASS
TS-09 | 201 | F the queued start ran after the stop completed (ready 2 times) | PASS
TS-09 | 202 | I the capture starts anyway (1.2.3 refused to start at all) | PASS
TS-09 | 203 | I transmit reported as unavailable, non-fatal: "H2C playback: the device node /tmp/loopback_emu_3881/no_such_iwfg1 doe" | PASS
TS-09 | 204 | I capture delivers (29360128 samples) | PASS
TS-09 | 205 | J no transmit helper at first | PASS
TS-09 | 206 | J ensureH2c() starts iwfg_h2c on demand | PASS
TS-09 | 207 | J and it streams | PASS
TS-09 | 208 | J tone received 9.999847 MHz | PASS
TS-09 | 209 | c2h exit: driver error recognised | PASS
TS-09 | 210 | c2h exit: reader closed recognised | PASS
TS-09 | 211 | c2h exit: signal recognised | PASS
TS-09 | 212 | c2h exit: start-up failure recognised (not restarted) | PASS
TS-09 | 213 | c2h rate line parsed: 2416.93 MiB/s | PASS
TS-09 | 214 | H2C stall lines recognised | PASS
TS-09 | 215 | ladder: 1 MiB default -> 256 KiB -> 64 KiB -> 16 KiB -> stop | PASS
TS-09 | 216 | transmit guard: 4 ch x 200 MSPS -> 2 ch; 2 and 1 left alone; 4 x 250 MSPS -> 1 ch | PASS
TS-09 | 217 | PL GPIO modes: 1 ch -> 1, 2 ch -> 2, 4 ch -> 3 | PASS
TS-09 | 218 | measured rate -> channels: 1500 -> 2, 760 -> 1, 3040 -> 4; an overloaded 2417 is not read as a count | PASS
TS-10 | 219 | H2C CONTROL action present | PASS
TS-10 | 220 | control window opened | PASS
TS-10 | 221 | Transmit tab: H2C playback helper running, waiting for the generator | PASS
TS-10 | 222 | generator FIFO follows the backend's (/tmp/app_live_emu_4034/h2c.fifo) | PASS
TS-10 | 223 | Start generator button | PASS
TS-10 | 224 | H2C playback row: streaming | PASS
TS-10 | 225 | H2C to card row: iwfg_h2c's measured rate shown | PASS
TS-10 | 226 | C2H capture row: delivered vs needed shown | PASS
TS-10 | 227 | Received row: the received tone matches the generator's frequency | PASS
TS-10 | 228 | Verify loopback: "✓ Loopback verified. The generator moved 7.300 MHz and the tone received through the ADC moved 7.299 MHz. The " | PASS
TS-10 | 229 | Start/Stop actions present | PASS
TS-10 | 230 | Stop returned in 0 ms | PASS
TS-10 | 231 | Start returned in 7 ms (helper pre-flight no longer freezes) | PASS
TS-10 | 232 | the injected C2H driver error fired | PASS
TS-10 | 233 | no dialog for a recovered capture helper | PASS
TS-10 | 234 | transmit streaming after the restart | PASS
TS-10 | 235 | Verify loopback after the recovery: "✓ Loopback verified. The generator moved 7.300 MHz and the tone received through the ADC moved 7.299 MHz. The " | PASS
TS-10 | 236 | injected: the card stops delivering C2H data (c2h_stream waits in the driver) | PASS
TS-10 | 237 | after ~5 s with no capture data the GUI resets the device by itself | PASS
TS-10 | 238 | the reset finished: transmit closed first, capture after, both restarted | PASS
TS-10 | 239 | transmit streaming after the reset | PASS
TS-10 | 240 | no dialog for a recovered device | PASS
TS-10 | 241 | Verify loopback after the reset: "✓ Loopback verified. The generator moved 7.300 MHz and the tone received through the ADC moved 7.299 MHz. The " | PASS
TS-10 | 242 | sdr_backend.log records the helper output and the recovery reason | PASS
TS-10 | 243 | the GUI thread never froze (longest heartbeat gap 210 ms) | PASS
TS-10 | 244 | closing the window took 160 ms | PASS

## Bench Record
Bench Record (BT)
Fill in the yellow cells on the target board. Result: choose PASS / FAIL / N/A. Example of the expected format: BT-04 Measured = 'Gen3 x8'.
ID | Test | Objective | Procedure (summary) | Expected result | Measured / observed | Tester | Result | Date | Remarks
BT-01 | Package integrity | Confirm the delivered package is complete and unmodified. | Set-up: Host with the package extracted. 1. Run TS/02_Scripts/verify.sh from the package root. | RESULT: PASS: manifest matches, 37 firmware files, 13 contract checks PASS.
BT-02 | Firmware boot and ABI | Confirm that the complete firmware set is running. | Set-up: Board booted from the BOOT.BIN built from FF; UART0 console at 115200 8N1. 1. Power-cycle the board. 2. Capture the console log. | [init] DAC input = DDS compiler and [pcie] pcie_cfg ABI 4 ... caps 0x7F are printed. There are no init errors.
BT-03 | Driver load and device nodes | Confirm that the iwfg QDMA driver binds the card. | Set-up: Host with kernel headers; card enumerated (lspci). 1. make in SC/01_sdr_workstation_GUI/drivers. 2. sudo insmod iwfg.ko. 3. ls -l /dev/iwfg*; dmesg ¦ grep -i iwfg. | /dev/iwfg0 and /dev/iwfg1 exist. There are no driver errors.
BT-04 | GUI launch and PCIe pre-flight | Confirm the GUI detects the link. | Set-up: GUI built from SC (or BN binary). 1. Start sdr_workstation; select Live — PCIe DMA, /dev/iwfg0, cs16, 4 channels, 200 MSPS. | The link-discovery screen shows the driver, the nodes, and the PCIe link speed and width, then continues on its own. Record the link speed and width.
BT-05 | RFDC attach, ping and register sync | Confirm the PCIe control mailbox works end to end. | Set-up: GUI running; H2C CONTROL ▸ RFDC tab. 1. Press Attach. 2. Press Ping. 3. Observe the register readout. | Ping is acknowledged. Every register is read back, and the readout reports ABI 4.
BT-06 | Boot defaults readback | Confirm the board boots at the documented operating point. | Set-up: Freshly powered board; RFDC tab attached. 1. Read the ADC/DAC rates, decimation, interpolation, NCO, DDS, DSA, VOP, DAC source, PL GPIO mode and AXIS routing. | 4800 / 9600 MSPS, ×24 / ×24, NCO 3100 MHz, DDS 10 MHz, DSA 0 dB, VOP 32 mA, DAC source = DDS, GPIO mode 3, routing 0x1237.
BT-07 | DDS tone reception | Confirm the receive chain with the on-chip source. | Set-up: DAC output looped back to an ADC input through attenuation; DAC source = DDS. 1. Start capture. 2. Read the peak frequency and level. | A single tone at the expected baseband frequency (DDS 10 MHz through the 3100 MHz NCOs; see TS-05). Record the level (dBFS).
BT-08 | ADC dynamic performance | Record the RF metrics at the boot configuration. | Set-up: As BT-07, with the Blackman-Harris window and FFT 2048 or larger. 1. Read SINAD, SNR, SFDR, THD and ENOB from the Measurements panel. | Record all values. The acceptance limit is to be agreed with the customer. Reference: about 11 ENOB bits observed on the bench at the correct configuration.
BT-09 | DAC input source switch | Confirm DDS ↔ host selection and readback. | Set-up: RFDC tab attached. 1. Set the DAC input to Host, then read back. 2. Set the DAC input to DDS, then read back. 3. Repeat with rfdc_ctl dac-source host¦dds. | The readback matches each selection; the chain view says confirmed by the device.
BT-10 | Host transmit | Confirm that generator samples reach the DAC continuously. | Set-up: DAC source = Host; generator: sine, 10 MHz, amplitude 0.9, Loop-coherent on. 1. Start the generator. 2. Read the H2C to card row. 3. Read the received tone. | H2C rate ≈ 762.9 MiB/s. The received tone sits at the coherent frequency (9 999 847 Hz at 1 MiB). There are no broadband disturbances.
BT-11 | Verify loopback | Confirm the received tone follows the generator. | Set-up: As BT-10, with the looped-back ADC routed to AXIS output 0. 1. Press Verify loopback. | ✓ Loopback verified: the received tone moves by the same amount as the generator.
BT-12 | Transmit guard | Confirm the capture is reduced while transmitting and restored afterwards. | Set-up: Capture 4 channels at 200 MSPS; RFDC tab attached. 1. Start the generator. 2. Read the PL GPIO mode and the capture rate. 3. Stop the generator. | While transmitting: GPIO mode 2, capture ≈ 1526 MiB/s. After the stop: mode 3 is restored.
BT-13 | Capture throughput per channel count | Measure the delivered capture rate. | Set-up: Capture-only session. 1. Run 1, 2 and 4 channels (GPIO mode 1/2/3) for 60 s each. 2. Record the MB/s value and dmesg overflow messages. | 1 ch ≈ 763 MiB/s and 2 ch ≈ 1526 MiB/s without overflow. Record the 4-channel result (above the host drain on the reference host).
BT-14 | Start / Stop responsiveness | Confirm the GUI never blocks. | Set-up: Live session with transmit and capture running. 1. Press Stop, Start and close the window, five times each. | Each action returns at once (< 1 s). sdr_backend.log shows H2C closed before C2H.
BT-15 | Helper recovery | Confirm automatic recovery from a helper failure. | Set-up: Live session with transmit and capture running. 1. pkill c2h_stream. 2. Observe the GUI and sdr_backend.log. | The capture helper is restarted and the display re-attaches, with no dialog. Transmit is not interrupted.
BT-16 | Command-line client | Confirm `rfdc_ctl` controls the board. | Set-up: rfdc_ctl from BN or SC. 1. rfdc_ctl ping 2. rfdc_ctl nco-freq both all both 3100 3. rfdc_ctl dump | Each command is acknowledged with 0x2A, error 0. dump decodes the last command.
BT-17 | Reset all to defaults | Confirm recovery to the baseline. | Set-up: Change the decimation, NCO and DSA first. 1. RFDC tab ▸ Reset all to defaults. 2. Read back as in BT-06. | All values return to the BT-06 defaults.
BT-18 | Recording and offline replay | Confirm that recordings are byte-exact and can be replayed. | Set-up: Live capture, 2 channels. 1. Record for 10 s. 2. Open the file in offline mode. | The file size ≈ rate × time. The replay shows the same spectrum, and the .meta sidecar restores the format and channel settings.
BT-19 | Serial menu | Confirm the console functions. | Set-up: UART console. 1. Menu 5 (rates), menu 11 (clocks), menu 17 (PCIe diagnostics). | The rates match BT-06. The stream clocks are reported, and the PCIe diagnostics complete.
BT-20 | Power-cycle persistence | Confirm the boot defaults return after a power cycle. | Set-up: Change the settings, then power-cycle. 1. Read back as in BT-06. | The BT-06 defaults are restored.